## Sheet1
Date | Line_Number | Spool_ID | Rack_Ref | Field_Status | Progress_Pct | Welder_ID | Remarks
2026-11-06 | 24-CW-001 | SP-101 | PR-04 | Erected & Bolted | 15 | W-04 | First spool hung on bay 1
2026-11-07 | 24-CW-001 | SP-102 & 103 | PR-04 | Erected & Bolted | 45 | W-04 | Two spools lifted and leveled
2026-11-08 | 24-CW-001 | SP-104, 105, 106 | PR-04 | In Progress (6/8 spools) | 75 | W-08 | Stopped at 15:30 due to crane breakdown
2026-11-09 | 16-DIS-002 | SP-DIS-01 | PH-01 | Fit-up on hold | 10 | W-12 | Waiting for 300# ANSI spiral wound gasket
2026-11-08 | 24-CW-001 | GJ-04 | PR-04 | Not Started | 0 | W-04 | Golden joint awaiting remaining 2 spools