## Sheet1
Pour_Date | Foundation_Tag | Location | Activity_Desc | QC_Inspection | Curing_Days | Status
2026-10-22 | Pad P-12 | Pump House | Poured M35 concrete (45 m3) | Passed | 1 | In Progress
2026-10-26 | Pad P-12 | Pump House | Curing and cylinder test 7-day | Passed | 5 | In Progress
2026-11-02 | Pad P-12 | Pump House | Final curing & NDT rebound hammer check | Certified OK | 8 | Completed
2026-11-08 | Ring Beam TK-101 | Tank Farm | Excavation and blinding concrete | Under Inspection | 0 | 65% Completed
2026-10-24 | Trench C-1 | Substation | Excavate underground electrical trench | Passed | 0 | Completed